## Issue report
Title: |  | Issue Report
Project |  | File Management
Environement |  | Development server(live)
Tester: |  | Jiad
URL |  | http://nvsl.suzu-service2.com/admin/index.aspx
Issue ID | Issue no | Module | Issue Short Summary | Steps to Reproduce | Expected Result | Actual Result | Issue Image | Priority | Tester Feedback | Checked By | Developer feedback | Tester Feedback
1 |  | Log In | Blank Username accepts during Login | 1.Go to the url 2.Remain blank the user name 3. remain blank the password 4.Click the log in button | Error should show for- input username & password | invalid Password | https://ibb.co/0nfkC0B | Medium | Input the username & password or other wise without fill the username & password the log in button do not work | Masud | Fix | OK
2 |  | Log In | The Log in Page Ui | Go to the login url | the Ui should look lookertive | Here most of the page portion is blank & the ui does not look that much lookertive | https://ibb.co/G5Ns4bH | Low | Please use the whole page for Ui design. the blank space does not look good. Try to make the design more lookertive. | Masud | No need
3 |  | Profile | Edit button on My profile Page- Not recognizable | 1.go to website 2.Login with valid Credentials 3. Go to My Profile 4. Observe the page | All Button and Option should be Clearly visible and Recognizable | Edit Button is very Tiny and not Recognizable. | https://ibb.co/8jb22CM | Medium | Edit Button size can be bigger and Give Button Name to recognize easily | Masud | Fix | OK
4 |  | Project List | Button Name "Active" not Showing properly | 1. Goto the Website 2.login 3.Click Project List 4. Observe Button (Active/Inactive) | Button Name not showing properly | Button Name should be visible properly | https://ibb.co/7bKDyxm | High |  | Masud | Fix | OK
5 |  | Project List | "Update Project" Button/Option not showing for All Projects | 1. Goto the Website 2.login 3.Click Project List 4. Observe Button (Update Project) for All Project | "Update Project" Option is not showing for All Projects | Update should be shown for All projects | https://ibb.co/6w5hxpY | High |  | Masud | Fix | Edit/Update Button not Available for all projects from admin panel.
6 |  | User | Spelling Mistake on User Type | 1. Goto the Website 2.login 3. Click User 4. Observe the User Types | User Type: Tema Member, Tema Leader | Should be Team Member/ Team Leader | https://ibb.co/W3zfFF8 | High |  | Masud | Fix | OK
7 |  | Service Panel | Color Mismatch between Side Bar and Selected Color | 1. Goto the Website 2.login 3.Click settings from the top right position. 4. Choose Black-Ash color from Dark Side Bar | Color Mismatch between Side Bar from Selected Color | Color should Match between Side Bar and Selected Color | https://ibb.co/Kbv0C3p | Medium |  | Masud | No need
9 |  | Team Lead Dashboard | Team Lead can see Admin log | 1. go to website 2. login as team lead 3. select Project 4. Observe Login Log, Update log and File Log | Team Lead should See only His/Her own and His/Her team Members Logs | Team Lead can see All User's log Including Admin | https://ibb.co/W69h3Cp | High |  | Masud
10 |  | Dashboard- Login Log, Update Log, File Log | In the There are no Button to complete the date and time selection | 1. go to website 2. login as any user 3. select Filter from Login log, Update log or File Log 4. Click on Calender to Set Time and Date | Time Selection should Complete after clicking date and Time or There should be a Ok or Save button to Lock the selected Date and Time | Time selecting not completed after click on the time and date from The Calender | https://ibb.co/MZpR3W7 | Medium |  | Masud | This is the HTML control and selection method as it is. After change date or time you need to click ok or out side this control
11 |  | Admin>Edit My Profile | fail to update "Edit My Profile" for Admin | 1. go to website 2. login as Admin 3. select My Profile> Edit 4. Change any Data or Photo 5. click Save | Data or Photo Should Be updated Successfully | Showing Error- "Object reference not set to an instance of an object." | https://ibb.co/fN3g75y | High |  | Masud | Fix | OK
12 |  | Dashboad- Team lead & user | Team lead & Team Member can see the admin all log details. | 1. go to website 2. login as Team Lead or Member 3. Observe the Dashboard | A team lead can see his teamates log information & the Member can see his own log information only. But they both should not access to admin log information. | Here all User can see others all log files. | https://ibb.co/84Hr0y7 | High |  | Masud
13 |  | Admin User ( User page) | All user mobile Number PATTERN is valid or not | 1.Go to the url 2.sign in 3.click the user button 4.add user 5.go to the mobile number option in the sheet | There are should be a valid pattern of a mobile number | Here the mobile number pattern is invalid | https://ibb.co/ZJPLQsm | High | Here we fixed the phone number pattern with+880 or fix the number digit 11 not more than. A ivalid phone number is 11 digit not more than it | Masud | Fix | OK
14 |  | Admin User ( User page) | Multiple teamlead assign in a single project | 1.go to the url 2.sign in as admin 3.click the user button 4.go to search button 5.find akash sqard | There should be one team lead in a single team | Here we can assign multiple team lead in a single project | https://ibb.co/TvkGgPL | High | Here we can assign a single teamleader in a single project. If we go to add a multiple person add as team leader in a single team there shuld show some error. | Masud | Team lead role user wise not project wise
15 |  | Admin User (User page) | (Team lead , team member) in those words the spelling of team is showing wrong | 1.go to the url 2.sign in as admin 3.click the user button | The spelling of team should be "Team" | Here we can see that the spelling of team is tema which wrong | https://ibb.co/2YsrRwC | High | Please correct the Spelling of team | Masud | Fix | OK
16 |  | Admin User (User page) | The add user form does not update after click the cross button. | 1.go to the url 2.sign in as admin 3.click the user button 4.go to add user 5.Then input something 6.Then click the cross button 7.Show the result | After Click the cross button the page should be refreshed , its open a new page | Here after click the cross button it remains the same page, the page does not update, It open a previous page. | https://ibb.co/Q6314jV | High | After click the cross button it should open a new page | Masud | It;s not updateing until click ok/save button
17 |  | Admin | Admin can't remove user only can update | 1.Go to the url 2.log in as a admin 3.go to user page | there are should be remove button to delete user | there are no delete/remove button |  | High | please add a remove/delete user button | Masud | any data deletion isnot aceptable
18 |  | Team>Search | Search function is not working on Team Page | 1. Go to website 2. login as Any User 3. Select Team 4. click on Search. 5. Search by a exact or Similar Team Name | Exact or similar Team Should show | Showing all Team which is not similar with search keyword. | https://ibb.co/RHRJfmY | High |  | Masud | Here the serach keayword match all table content not only team name
19 |  | Team Lead> user | Team leader can not remove his user from the team | 1.Go to url 2.log in as a team lead 3.go to user | there are should have delete member button to remove member from the team | There is no remove / delete button |  | Medium |  | Masud
20 |  | file upload | team member can not upload zip/rar/exe extension file | 1.go to url 2.go to file upload | there are should be a option for .exe/zip/exe file upload | there are no a option for .exe/zip/exe file upload |  | Medium | please add a option for exe/zip/rar file upload | Masud | File tipe is fix as(all kind of Document, xml, json, image) | OK